## Sheet1
Club Reduce 4.0
Doctors Membership Website (External)
Website Section | Assigned To | Linked | What's Left | Libby's Subtasks | After Release | Time Estimate
Front Page Design |  | n/a | Are we happy with the design? | need new before and after pictures (don't photoshoot people who don't grant release), redesign front page, change buttons on bottom, update sliding photos with new testimonials, change font, we want size to fit on screen in 100%
Free Seminar | Libby | No | Link and Function (applied to "Attend Weight Loss Seminar" button too) | Text messaging (day of confirmation and day before), linked to existing site
Testimonials |  | No | Link, Function, Adding New Testimonials? | grid/better design (Janelle), customizable for doctors, add new testimonials from photoshoots
Reviews |  | Yes | Are we happy with the design? | have Janelle review
Services |  | Yes | Apply New Style (create something unique for headline?), Update Content (Info and images are old.) Are there services/treatments missing? Is this page sufficiently customizable for doctors? | we need lipo laser and lipo light, (lower priority)
About Us | Janelle | Yes | The description for Lighthouse Health needs to be updated. Also, is it customizable? | database issue, janelle is pretty close, add a staff (clinic) photo, update about us
Contact Us |  | No | Do we need both About Us and Contact Us? How do they differ? | add google plus/google map on page (low priority)
Success Stories |  | Yes | Design is wonky. Videos are old. Is this the same as the "Testimonials" tab? | add new videos
Free Weight Loss Report |  | Yes | Update Page Content, Free Report, and Email Campaign (Will this work for our doctors?) | not working for older doctors | update report and emails later
More About Us |  | Yes | Are we happy with this video? | can't hear people in more about us video (need to create new video with better sound and testimonials)
Doctors Membership Website (Internal)
Website Section | Assigned To | Linked | What's Left |  |  | Time Estimate
General Edits | Libby | n/a | Make sure breadcrumbs work. Stop sidebar from retracting after second click.
DASHBOARD | Libby | No | Finishing Functionality, Testing Functionality, Checking Each Page and Making Sure We're Happy with Design, Making Each Page Correspond with Staff Training (Where does the Scheduler connect/factor it?) | Re-direct loops, fake subdomain handler, table structure changing, old database versus new database functionality, lead tracking system: what happens to a patient when they become a lead, current status of each patient (can jump them to another status) | need a visual of the patient pathway
CLINIC TOOLS |  | Yes | Page Design?
[Paperwork] |  | Yes | Need to update style.
[Patient Profiles] |  | No | What does this require?
[Symptom Assessment] | Libby, Tessa, Janelle | No | Tessa Needs to Finish Basic Edits to Female, Edits Need to Be Approved and Discussed with Doc, Edits Need to Be Approved and Discussed in Scrum, Edits Need to Be Applied to Male, Assessment Needs to Updated in Doctors and Patients Website, Calculation Errors Need to Be Fixed |  | Neuro version of symptom assessment, make it have recommended products and/or programs, it prints differently than it appears online
[Assessment Results] | Libby | No | What does this require?
[Nutritional Reference Guide] |  | Yes | Need to decide on and update style. Nutritional Reference Guide itself also needs to be updated.
SEMINARS |  | Yes | Page Design?
[Upcoming] |  | No | Functionality and Design
[Attendees] |  | No | Functionality and Design
[Locations] |  | No | Functionality and Design
PATIENTS |  | Yes | Page Design?
[Office Visits] |  | No | Functionality and Design
[Manage Patients] |  | No | Functionality and Design
MARKETING |  | Yes | Page Design?
[Planner] |  | No | Functionality and Design
[Calendar] |  | Yes | Testing Functionality, Update Heading to New Style | subcategories: trade show, clean naming convention | re-code monthly marketing planner (add a miscellaneous category)
[ALL] |  |  | Re-Linking and Testing All Files and Pages, Deciding on Style for Child Pages, Updating/Re-reviewing Content in Each Section, Addressing Content HOLES: Billboards, Bridal Parties, Club Reduce TV, Cooking Classes, Dinner Program, Email Blast, Email Template, Graduate Classes, Home Parties, Learn & Lose, Lumpy Mail, Patient Appreciation Events, Snail Mail, Social Media | Email Blast: if we could find another server (make everyone you want to send to opt-in first), decide strategy, thumbnails on banners
[Weight Loss] |  | Yes | Same as "ALL"
[Pain/Neuropathy] |  | Yes | Same as "ALL"
[Additional] |  | No | Linked to Wrong Page, Needs to Be Taken Down/De-Activated
[Maintenance] |  | No | Need to Update/Re-Do Maintenance Promotion Materials / Learn & Lose
PROGRAMS |  | Yes | Page Design?
[Weight Loss] |  | Yes | Re-Linking and Testing All Files and Pages, Adding New Basic Training Videos for Each Program, Updating/Overhauling Additional Programs: 20-Day, 3-Week LipoLaser, 3-Week LipoLight, 12-Week Ultimate Weight Loss
[Pain/Neuropathy] |  | Yes | Re-Linking and Testing All Files and Pages, Adding New Basic Training Videos for Each Program, Updating/Overhauling Additional Programs: Knee Pain, 8-Week Fibro, Pain-Free Now
[Additional] |  | Yes | Re-Linking and Testing All Files and Pages, Adding New Basic Training Videos for Each Program, Updating/Overhauling Additional Programs: 30-Day Clear Skin, 5-Week Diabetes, 5-Week Gluten-Free, Hormone Balancing, Insomnia Solutions, Quit for Life, Stress-Free Lifestyle
[Maintenance] |  | Yes | Re-Linking and Testing All Files and Pages, Adding New Basic Training Videos for Maintenance, Updating/Overhauling Maintenance Protocol Sheets
TRAINING |  | Yes | Page Design?
[Success Checklist] |  | Yes | Complete Re-Design?
[Quickstart] |  | Yes | Complete Re-Design? Add Additional Content?
[Basic Training] |  | Yes | New Style, Re-Linking and Testing All Files and Pages, Recording, Editing, and Adding New Basic Training Videos, Developing Content/Filling Holes: All Lessons
[Staff Training] |  | Yes | New Style, Re-Linking and Testing All Files and Pages, Recording, Editing, and Adding New Training Videos, Developing Content/Filling Holes: Most All Positions, Checking that Content Corresponds with Dashboard
[Webinars] |  | No | Link It Up, Check Functionality, Review and Cut Old Webinars
[Summit] |  | Yes | Re-Linking and Testing All Files and Pages
PRODUCTS |  | No | Compile Information, Check that Pricing Matches Solutions4 Pricing, Write New Desc. For Each Product, Update Product Images that are Outdated, Cut Old Products, Add Missing Products, Change 4 Program Options to 1, Establish New Design, Set Up New Cart with Functionality, Set Up Revised Cart with Functionality on Patient Site | Patient Purchase promotions, S4 email blast promotions, shopping cart needs to include coupon codes, add auto-ship, add video snippets, add "people who bought this also bought"
RESOURCES |  | Yes | Are we happy with the design? Content Needs to Be Updated, Someone Needs to Call and Get Affiliate Links for Everything
FAQ |  | No | Link, Functionality, Test, Add Content?
Patient Membership Website
Website Section | Assigned To | Linked | What's Left |  |  | Time Estimate
External |  | n/a | Do we want any differences between Doctor and Patient versions?
Dashboard |  | No | Are we happy with the design? Functionality and Testing, Symptom Assessment Updates/Revision Need to Be Applied | add patient visit data (needs to link)
Patient Profile |  | No | What does this require?
Solutions4 |  | No | All Shopping Cart tasks described above, plus customization to patient site. Functionality and Testing.
Cook'N |  | No | Updating recipes, stage 2 editing process, establishing account/deal with Cook'N
Classes |  | Yes | Updating style/design of parent and child pages, uploading additional cooking classes with photos, re-editing and adding CR TV episodes, Learn & Lose isn't linked and isn't complete (only up to Lesson 20) - requires writing, editing, finalizing, recording, editing, and putting up; there's the email sequence too
Newsletter |  | Yes | Are we happy with design? Add 2015 newsletters (revising their PDF form and uploading), All of Pain-Free Lifestyle has to be re-done (PDFs were made incorrectly)
FAQ |  | No | Link, Functionality, Test, Add Content?
Club Reduce TV |  | Yes | Is this still what we want?
ADDITIONAL BACKEND PROJECTS
Project | Assigned To | Linked | What's Left |  |  | Time Estimate
Database Updates | Tessa, Janelle | n/a | Ongoing; however, large amount of Additions/Deletions/Edits/Errors need to be applied and then checked.
Email Campaigns |  | n/a | Unknown -- Need to Dive into InfusionSoft and Find/Compile All Active Email Sequences and Find Out What Needs to Be Done, Update/Re-Write Program Emails, Create E-Newsletter Campaign that's Customizable for Doctors |  | need to fix bugs and errors in email campaigns
Crossover Plan and Implementation | Libby | n/a | How? When? Issues?
Admin |  |  |  | Bugs, needs to re-written, need a support person who knows how to do things | figure out how to show doctors emails, telling doctors which emails have hard bounces (we don't get the info back from infusionsoft, something that marks emails "success" or "failed"), need a support person for after launch, re-write seminar registration
Text Messaging |  |  |  | Set Up an account, a way to charge the doctors, 6 Division, charge 5 cents per message
Help Videos | Libby/Dayo/Tessa |  | Initial set up training |  | expanded how-to every page training
Ask Libby where to put:
Integrate the Scheduler
Nutritional Reference Guide App